| Site | Priority | Project Description | Status | Estimated Completion Date |
| --- | --- | --- | --- | --- |
| AE |  | Chapter I Bldg- Install Partition | Wall installation complete-Pending installation of door jams | Aug 15,2004 |
| AE |  | Principal Office | Door relocation | Work request on hold (not approved). |
| AE | VI | Nurses Office | Doorway to new office | Aug 31, 2004 |
| AE | II | Nurses Office | Install refrigeration unit- | Complete |
| AE |  | Mid-Bldg. | Locker removal | On Hold. |
| AE | IV | Water Supply | Back Flow Prevention, Device installation | On Hold |
| CHE | VI | Barracks Bldg. Repairs | Partition for E-Wing office | Materials on order. Scheduling in progress. |
| CHE | IV | Barracks Bldg. Repairs. | Priority # 54, 57, 96. #57 Room is being redone. Floor has material rot on perimeter walls. | Scheduling in progress. |
| CHE | IV | Barracks Bldg. Repairs. | Bathroom floor repair Will be identified & prioritized by building mechanic. Pending Barracks | Scheduling in progress |
| CHE | IV | Barracks Bldg. Repairs | Repair porch ceiling | Complete. |
| DT |  |  | Various floor covering replacement | 2nd bldg. complete |
| DV |  |  | Various floor covering replacement | Port. 1,2,3,4 complete |
| LU |  | Irrigation Well | Replumbing for irrigation purposes | Request on hold. |
| LU |  | Wastewater System | Connect to Community System | June 2005 |
| LM | IV | Barracks | Need sub floor repairs/renovations. Exterior wall repair/stucco. | Awaiting for direction and funding from CMT. |
| LU |  | Temporary Parking on EBID, Right of way | Parking on drain levy will need to be rebuilt due to EBID-maintenance on drain | Complete |
| SM | IV | Wastewater System | Monitoring of system operation- Leach Fields are showing signs of failure. | Will continue monitoring and working with E.I.D to determine repair & schedule. |
| SM |  | Relocate Additional Portable Classroom | Preparing utilities connection for portable relocate from Chap. Mid. | Est. Comp. date Oct 31, 04 |
| SP |  | Office Area | Counter top & floor covering replacement | Complete |
| GMS | III | Board Room | Carpet replacement | Complete |
| GMS | III |  | Carpet &ceramic tile replacement throughout bldg. | Est. Comp. Date Aug 3, 2004 |
| STM |  | Choir Room | Ceiling, Mechanical & Electrical | In Progress |
| GHS | VI | North Bldg. | Doorway cut-need Jam floor repairs | Complete |
| GHS |  | Auto Mechanics Classroom Shop | Install lift (vehicle) | On Hold |
| GHS | IV | Wastewater treatment plant. | Need to replace main transfer pump | Pump on order |
| GHS | IV | Swimming pool | Circulation pump is in need to schedule work | Replacement unit on order-Oct 30, 04 |
| GHS |  | South side perimeter fence repairs | Replacement-estimated cost $8,000.00 | On hold for next years funding (SB-9) |
| STHS | IV | Replacement lockers for fire damaged unit | Will relocate units from Anthony Mid Bldg. | Est. Comp. Date Aug 31, 2004 |
| Motor Vehicle Shop |  |  | Complete Shop Expansion | On hold |
| Motor Vehicle Shop |  | Auto Shop Supervisor | Build Office for Supervisor ( Transportation Clerk is in current office) | On hold |
| DP | III | Center barracks | Remodel center barracks into three classrooms | Complete |
| DP | III | Conference room portable | Install partition in conference room portable. As per Mr. Y, partition not needed | Material on order Aug 31, 2004 |
| DP | IV | Portables | Install water fountain in all portables | Work request under review |
| GAC | VI | Building Repairs | Miscellaneous mechanical & electrical repairs | In progress |
| GAC | VI | C-wing conference room | Demo complete floor covering complete-wall repair in progress | Date. Complete June 17, 04. |
| GAC |  | Dining room | New floor covering, installation of temporary wall. | On Hold |
| GAC |  | Site mobile home installation | Identifying utility hook-ups for site mobile home installation for security. | Utilities locating in progress |