## SPCE.PROJ. PENDING
Site | WO# | Project Description |  | Estimated Completion Date
AE-Pre-K | 99575 | Threat Assessment | Installation of new fencing | Completed 5/30/13
DT | 102469 | Portable | Portable Relocation # 39 DM from San Miguel | Portable Relocation Complete
Pending Utilities and Sidewalks
CHM | 100728 | Football | Installation of new scoreboard | Completed 7/8/13
GAC | 99743 | Electrician/Plumber | Purchase of new Morgan Building | On order
GHS/GMS |  | Wastewater Line | Renewing permit for placement of utilities in public right of way | IBUC & NMDOT Permit renewed -
|  |  | So we can obtain a work permit to repair the line suspended on | Start work on June 1, 2013 - 85% Complete
|  |  | the River Crossing. | Scheduled Completion July 2013
GMS | 101816 | Vocational Bldg | Abate asbestos vct - install new vct | Completed abatement
Installation of new tile in-progress.
MQ | 79890 | Playing Fields | Provide water for irrigation of playing fields. | Started on project - Pending Summer
Need to install new irrigation system.
MQ | 85440 | Multi-Purpose Room | VCT Floor covering to be replaced with new. | Completed 6/27/13
MQ | 99968 | Room 107 | Abate asbestos vct - install new vct | Completed
PPD | 99749 | Roof Repairs | Auto Shop, PPD and SNP Warehouse | Completed
STE | 97636 | Art Room | Purchase of new Morgan Building | On order
District Wide |  | Pre-K Centers | Build raised planters at sites. | 2013-08-01
AE, CHS
LM

## 12-13 Completed Projects
DT | 86324 | Portable Relocation | Relocate Portable # 92 DM from Chap Mid | Relocation of unit complete on 5/9/12
Utility connection in progress - Complete
LL | 86323 | Portable Relocation | Relocate Portables # 2DW and 80DW from San Miguel Elem to LL. | Complete
CHE | 90921 | Nurses Room | Abate asbestos containing floor mastic and retile. | Complete
CHS | 88266 | North Parking Lot | Repair buckled sidewalk | Complete
CHM | 90894 | Outside Water Fountain | Lay concrete, provide domestic water and electrical . | Complete
90897
90898
District Gyms |  | Gyms | Re-finish all district Gyms not including GHS Boys & Girls Gym. | Complete
VE |  | Dumpsters | Pour concrete slabs | No Action Taken 10/15/2012
AE | 90832 | Provide sidewalks | connecting to existing and landing concrete pad | Complete
to meet ADA requirements.
GAC | 83845 | Main Entrance | Install new iron gates | Complete
DT | 92316 | Need Fence between | front and back of school | Complete
GMS | 92521 | Gym | Need metal cages to separate storage. | Completed 10/31/12
PPD | 74236 | Barracks | Install fencing for furniture control. | Completed 11/19/12
DP | 91169 | Portable 32DW | Provide electrical, water and sewer and install evaporative a/c unit. | Complete
91170
91171
| 94720 |  | Need to redeck portable when abatement is complete. | Completed Abatement - Pending Floor and Tile
DP | 94720 | Portable 32DW | Need to redeck portable when abatement is complete. | Complete
DP | 97404 |  | Removal and concrete cutting. | Complete
DT | 94686 | Sanchez Portable | Concrete around portable and surrounding area. | Complete
STHS |  | New Laser Machine | Install power and vent . | Complete
District Wide | 97928 | Office | Installation of door bells as per Threat Assessment. | Complete
Elementary | 97929 |  |  | DV,LL,LU,NV,RS,STE,SP,VE and Pre-K's
Schools | 97936
97935
97756
97930
98442
97938
97931
97932
97933
District Wide | 97758 | Office | Installation of door bells as per Threat Assessment. | Complete
Elementary | 97759 |  |  | DV,LL,LU,NV,RS,STE,SP,VE and Pre-K's
Schools | 97939
97937
97934
98655
98656
98700
98652
RS | 97414 | Grounds | Need to remove shrubs (safety) | Complete
GHS | 50365 | Leadership Project | Requested by Mr. Grace on behalf of the Facilities Goal Team for the | Completed - Spring Break
Entire Campus-Metal doors, rails, poles need to be painted maroon.
District Wide | 96027 |  |  | STHS - Complete
CHS, GHS, STHS | 96543 |  |  | GHS - Complete
96526
AE-Pre-K | 100051 | ADA | Pour new sidewalk | Completed 5/7/13
DT | 100536 | Threat Assessment | Installation of new fencing w/gates | Completed 5/14/13
GHS | 99864 | Soccer Field | Demo and removal of existing concrete and pour new concrete | Completed 4/17/13
w/ADA requirements along w/new sidewalk
RS | 93203 | Mobile Home Space | New fence will be installed in this area to store equipment | Completed 4/19/13
(i.e. Tractor, District Vehicle and Lawnmower)
District Wide | 96024 | Baseball/Softball Fields | Purchase and Installation of new scoreboards. | CHS - Complete 4/16/13
CHS,STHS | 96016 |  |  | CHS - Complete 4/17/13
GHS
GHS | 101134 | Soccer Field | Double gates for new ADA sidewalk | Complete 5/30/13
LU |  | Classrooms | Painting classrooms as contractors finish remodeling | Complete

## 11-12 Completed Projects
GHS | 68457 | Leadership Project | Purchase and install new marquee. | As per R. Gallegos he will provide one
in the next Construction Phase.
STHS | 73071 | Leadership Project | Purchase and install new marquee. | Asp R. Gallegos he installed one with the
paving project.
San Miguel | 74386 | Repair all domestic | and mechanical water lines that froze due to Winter Storm 2011 | Domestic is complete, Pending mechanical
This project will be completed by Construction Dept. Summer 2012
LU |  | Playing Fields | Provide water for irrigation of playing fields. | 100% Complete
CHS | 67120 | Leadership Project | GYM - Need to re-stripe and refinish floor. | Complete 7/14/11
GHS | 40695 | Leadership Project | Girls Gym - Need to check heating and control dampers in gym. | Completed 7/6/11 - Coils are ok will change filters
in the winter.
GMS | 68436 | Leadership Project | Purchase new football scoreboard and install (Leadership Council | Completed on 5/24/11
GMS | 68432 | Leadership Project | Entire Campus around and in between all buildings level all ruts | Completed on 5/25/11
and bumps - backfill against sidewalks, clean out all storm drains.
STMS | 65036 | Leadership Project | Need electrical outlets for new CPU Lab in room 19 | Completed on 3/24/11
STMS | 68427 | Leadership Project | Repaint Flashing/cap on parapet wall both North & South buildings. | Completed on 7/14/11
STMS | 71952 | Leadership Project | North/South Bldgs - Need to abate (asbestos) in various areas then | Completed areas in North Bldg where there is
|  |  | re-tile. | no asbestos.
SM | 75469 | Asbestos Abatement | Abate approximately 100ft of Asbestos containing insulation so we can proceed with water line repairs caused by Winter Storm in Feb. | Complete
GHS |  |  | Replace 40" of broken sidewalk - Safety Issue | Complete
STE |  | Parking Lot | Seal cracks | Complete
STHS | 75574 | Tennis Courts | Repair Cracks | Complete
GAC/AE | 78258 | Morgan Building | Relocate 12' x 16' from GAC to AE - SPED Bldg | Complete
STMS |  | Fencing | New fencing on entrance of South Gate and Portables on Northend. | Complete
Purchasing | 77261 | Extend the concrete slab outside both garage door in the purchasing warehouse. |  | Complete
Warehouse
CHS | 80270 | New Laser Machine | Install power and vent .
Complete
CHS | 82084 | Gym | Straps and cables for basketball goals are in the way when shooting. | Complete
Need to relocate safety straps and cables on both courts
GAC-Pre-K | 83058 | Pre-K Classrooms | Replace counter tops with new ones to include fixtures. | Complete
GHS | 56579 | Leadership Project | Please plan for this summer to paint all frames and seal | Complete
all doors in the North Bldg, to include caulking of the new doors.
GHS | 78153 | Running Track | Rubberized surface needs to be repaired and repainted. | Complete
Track repairs are complete, Polyurethane application will be
postponed until late March due to cold weather.
GMS | 68430 | Leadership Project | Paint mascot on Gym floor | Complete
MQ |  | Original Building | Abate asbestos containing floor covering (VCT) and install new | Complete
VCT.
STHS | 78155 | Running Track | Rubberized surface needs to be repaired and repainted. | Complete
Track repairs are complete, Polyurethane application will be
postponed until late Feb or March due to cold weather.
Several Locations | 78663 | Chaparral HS - Field House, Gadsden ES, Gadsden HS (Admin, Library, V-Gym) and |  | Complete
| 78664 | STHS - Gym Equipment Data Collection Inventory and Data for use in setting up
| 78665 | Preventive Maintenance Program on equipment.
78666