## SPCE.PROJ. PENDING
Site | WO# | Project Description |  | Estimated Completion Date
DT | 102469 | Portable | Portable Relocation # 39 DM from San Miguel | Portable Relocation/Utilities Complete
Pending Flooring and Sidewalks
DT | 103357 | Portable | Relocate fence. | Complete 8/9/13
GAC | 99743 | Electrician/Plumber | Purchase of new Morgan Building | On order
GES | 103285 | Campus | Raise west fence 3" higher to prevent vandalism. | Scheduled for August 12 - 15, 2013
GHS/GMS |  | Wastewater Line | Renewing permit for placement of utilities in public right of way | IBUC & NMDOT Permit renewed -
|  |  | So we can obtain a work permit to repair the line suspended on | Start work on June 1, 2013 - 85% Complete
|  |  | the River Crossing. | Scheduled Completion September 2013
GMS | 101816 | Vocational Bldg | Abate asbestos vct - install new vct | Completed abatement
Completed VCT 7/15/13
LM - Daycare | 105965 | Daycare Area | Painting and clean up of daycare rooms. | Scheduled Completion September 1, 2013
MQ | 79890 | Playing Fields | Provide water for irrigation of playing fields. | Started on project - Pending Summer
Need to install new irrigation system.
STE | 97636 | Art Room | Purchase of new Morgan Building | On order
District Wide | 99576 | Pre-K Centers | Build raised planters at sites. | 2013-08-01
AE, CHS | 99797
LM | 104223