## SPCE.PROJ. PENDING
Site | WO# | Project Description |  | Estimated Completion Date
CMS | 117085 | PE Locker Replacement |  | 2014-07-01
CH-Pre-K | 117087 | Playground | Replace sand with Engineered Wood Fiber | Complete
Fall Area
CH-Pre-K | 117023 | Playground | New cinder block barrier to separate sandbox from wood chips. | 2014-08-01
CHS | 93777 | Soccer Field | Install canopy shades | 2014-08-01
CHS | 116042 | Amphitheater | Remove and replace a section of concrete that is lifting. | 2014-08-01
DP | 117024 | Sanchez Portable | Install sink, counter and water heater for science lab. | 2014-07-01
Early College
GAC | 113757 | IT Office | Asbestos Abatement | 2014-06-01
Abatement complete - Painting and Floor
replacement in progress.
GHS | 116990 | Boys Baseball Field | Remove grass from diamond and replace with sod. | 2014-07-01
GMS | 108222 | Front Campus | Remove mulberry trees from planters and prep for planting. | Removal of trees & planting by others - Complete
Working on providing water source and electrical
for irrigation system.
GMS | 110835 | Permit | Acquire "Right of Use Permit" for 40ft of left bank of Anthony Drain | Estimate Completion June 2014
|  |  | for parking access, fence and landscaping. | Fencing in progress
GMS | 117084 | C-Wing | Asbestos Abatement | 2014-06-01
GMS | 117147 | PE Dressing Rooms | Replacement of lockers in Boy & Girls | 2014-07-01
MQ | 111219 | Septic Tank | Demolish and remove abandoned septic tank and pumps. | 2014-06-01
STE | 112234 | Bus Turnaround | Metal canopy shades for students | 2014-08-01
STMS | 111739 | Fire Hydrants | Replacement of (5) Fire Hydrants | Complete