## SPCE.PROJ. PENDING
Site | WO# | Project Description |  | Estimated Completion Date
CMS | 117085 | PE Locker Replacement |  | Complete
CH-Pre-K | 117023 | Playground | New cinder block barrier to separate sandbox from wood chips. | 2014-08-01
CHS | 93777 | Soccer Field | Install canopy shades | 2014-08-01
CHS | 116042 | Amphitheater | Remove and replace a section of concrete that is lifting. | 2014-08-01
CHS | 119228 | Running Track | Repair worn rubberized surface, apply 2 coats to running track | 2014-09-01
and stripe running track.
GAC | 113757 | IT Office | Asbestos Abatement | Complete
GHS | 116990 | Boys Baseball Field | Remove grass from diamond and replace with sod. | 2014-07-01
GMS | 108222 | Front Campus | Remove mulberry trees from planters and prep for planting. | Removal of trees & planting by others - Complete
Working on providing water source and electrical
for irrigation system.
GMS | 117084 | C-Wing | Asbestos Abatement | Complete
GMS | 117147 | PE Dressing Rooms | Replacement of lockers in Boy & Girls | 2014-07-01
MQ | 111219 | Septic Tank | Demolish and remove abandoned septic tank and pumps. | 2014-08-01
STE | 112234 | Bus Turnaround | Metal canopy shades for students | 2014-08-01