## SPCE.PROJ. PENDING
Site | WO# | Project Description |  | Estimated Completion Date
STHS | 124792 | Football Field | New Scoreboard | 2015-06-30
STHS | 127644 | Softball Field | Batting cages for softball field please see Ms Contreras or Rick | 2015-05-30
GHS | 125861 | Softball Field | Batting cages for Softball Field | Framing Complete, pending nets
Alta Vista ECHS |  | C-Wing | Remodeling - Change signs, Windows, Asbestos Abatement-New Flooring | 2015-06-15
STHS | 131378 | Nurses Portable | Remodeling Clinical De Familia side for School Nurses, installation of | 2015-08-31
new restroom.
GAC - Prek | 127302 | Kitchen - Serving Area | Build a counter with sink and wall cabinets. | 2015-06-30
STHS | 130086 | Main Parking Lot | Replace chain link roll gates w/wrought iron gates. | 2015-08-31
Entry Gates
NV | 122505 | Bus Turnaround | Build shade canopy on East Side | 2015-07-31
NV | 113536 | Playground | Remove sand and fill in with wood chips. | 2015-08-31
LM - Pre-K | 113535 | Playground | Remove sand and fill in with wood chips and build curbs around | 2015-06-30
playground.
DT |  | Portables | Move in two double portables. | 2015-08-31
STHS | 132919 | Auxiliary Gym | Replace scoreboard with new one. | 2015-08-31