## SPCE.PROJ. PENDING
Site | WO# | Project Description |  | Estimated Completion Date
STHS | 127644 | Softball Field | Batting cages for softball field please see Ms Contreras or Rick | 2015-10-30
GHS | 134308 | Field Restroom | Re-roof, paint and install signage | Complete
STHS | 131378 | Nurses Portable | Remodeling Clinical De Familia side for School Nurses, installation of | Complete
new restroom.
NV | 122505 | Bus Turnaround | Build shade canopy on East Side | 2015-08-31
NV | 132916 | Playground | Install new shade canopies over playground. | Complete
STHS | 132919 | Auxiliary Gym | Replace scoreboard with new one. | Purchased
| 139969 |  | Install scoreboard. | Pending installation
STHS | 128389 | Tennis Courts | Re-condition playing surface | 2015-10-30
RS | 132046 | Marquee | Install new LED Marquee | 2015-10-30
STHS | 139966 | Marquee | Install new LED Marquee | 2015-10-30
LL | 136411 | Playground | Install wood chips in place of sand in playground. Replace plastic | 2015-10-30
curbs with cement.
LL | 137754 | Parking Lot | Repaint Parking lot including Handicap parking areas and fire lanes | Complete
GE | 137710 | Parking Lot | Repaint Parking lot | 2015-10-30
STHS | 139217 | Sewer | Major sewer line replacement in building (3 phases) | 2015-12-30