## SPCE.PROJ. PENDING
Site | WO# | Project Description |  | Estimated Completion Date
STHS | 127644 | Softball Field | Batting cages for softball field please see Ms Contreras or Rick | 2016-01-30
6
NV | 122505 | Bus Turnaround | Build shade canopy on East Side | 2016-01-30
STHS | 128389 | Tennis Courts | Re-condition playing surface | Complete
RS | 132046 | Marquee | Install new LED Marquee | 2015-12-31
STHS | 139966 | Marquee | Install new LED Marquee | 2015-12-19
LU | 140718 | Playground | Wood chips and concrete curbs | 2015-12-19
STE | 113441 | Playground | Wood chips and concrete curbs | 2015-12-31
STMS | 138255 | Gym | Acquire and install scoring table | 2015-12-19
STHS | 132037 | Parking Lot Entrance | New wrought-iron gate to entrance of parking lot. | Complete
STHS | 131970 | Football Field | New visitors bleachers to conform to code. | 2015-12-18
PPD | 129148 | Shops | Install upgraded electrical service for shop area. | Complete
PPD | 141679 | Maint Warehouse | Move maintenance distribution from old warehouse to new. | 2015-12-18
PPD | 128463 | Shops | Establish welding/small engine shop behind Auto Shop. | 2016-01-31
CHS | 141677 | Geothermal Lines | Repair of lines throughout building. | 2016-01-31
LU | 143295 | Mechanical Room | Replace old damaged water heater w/boiler system for domestic. | 2016-01-31
CHS | 141351 | Football Field | Install ADA accessible sidewalk at visitors side. | 2015-12-18
LL | 141373 | Classrooms | Install new VCT floor in 7 classrooms. | 2015-12-31