## SPCE.PROJ. PENDING
Site | WO# | Project Description |  | Estimated Completion Date
STHS | 127644 | Softball Field | Batting cages for softball field please see Ms Contreras or Rick | 2016-01-30
NV | 122505 | Bus Turnaround | Build shade canopy on East Side | 2016-02-29
RS | 132046 | Marquee | Install new LED Marquee | Complete
STHS | 139966 | Marquee | Install new LED Marquee | 2016-01-31
LU | 140718 | Playground | Wood chips and concrete curbs | 2016-01-31
STE | 140025 | Playground | Wood chips and concrete curbs | Complete
STMS | 138255 | Gym | Acquire and install scoring table | 2016-01-31
STHS | 131970 | Football Field | New visitors bleachers to conform to code. | Complete
PPD | 141679 | Maint Warehouse | Move maintenance distribution from old warehouse to new. | Complete
PPD | 128463 | Shops | Establish welding/small engine shop behind Auto Shop. | 2016-01-31
CHS | 141677 | Geothermal Lines | Repair of lines throughout building. | Complete
LU | 143295 | Mechanical Room | Replace old damaged water heater w/boiler system for domestic. | Complete
CHS | 141351 | Football Field | Install ADA accessible sidewalk at visitors side. | Complete
LL | 141373 | Classrooms | Install new VCT floor in 7 classrooms. | Complete
CMS | 143314 | Parking | Create location for trash bins at Bus Turn-around | 2016-01-31
RTC | 143605 | Portables | Install new floors to portable classrooms | 2016-03-31
District Wide | 145632 | District Wide | Repair all deficiencies found in Fire Sprinkler 2015 inspections. | 2016-03-31
GAC | 142171 | HVAC - Roofing | Repair damaged of (8) HVAC equipment on roof due to hail storm. | 2016-03-15
STHS | 145710 | Landscaping | Install raised planters | 2016-03-15