## SPCE.PROJ. PENDING
Site | WO# | Project Description |  | Estimated Completion Date
STHS | 127644 | Softball Field | Batting cages for softball field please see Ms Contreras or Rick | 2016-01-30
NV | 122505 | Bus Turnaround | Build shade canopy on East Side | 2016-02-29
STHS | 139966 | Marquee | Install new LED Marquee | Complete
LU | 140718 | Playground | Wood chips and concrete curbs | 2016-01-31
STMS | 138255 | Gym | Acquire and install scoring table | 2016-01-31
PPD | 128463 | Shops | Establish welding/small engine shop behind Auto Shop. | 2016-01-31
CMS | 143314 | Parking | Create location for trash bins at Bus Turn-around | 2016-01-31
RTC | 143605 | Portables | Install new floors to portable classrooms | 2016-03-31
District Wide | 145632 | District Wide | Repair all deficiencies found in Fire Sprinkler 2015 inspections. | 2016-03-31
GAC | 142171 | HVAC - Roofing | Repair damaged of (8) HVAC equipment on roof due to hail storm. | 2016-03-15
STHS | 145710 | Landscaping | Install raised planters | 2016-03-15
AVEC | 147971 | Portable Relocation | Move (3) Double Portables from DT to Alta Vista Early College | 2016-08-01
GHS | 146847 | Running Track | Perform deep cleaning of artificial turf and repair to running track and | 2016-08-01
re-stripe.
CHS | 146844 | Running Track | Perform deep cleaning of artificial turf and repair of running track. | 2016-08-01
STHS | 146848 | Running Track | Perform deep cleaning of artificial turf and repair of running track. | 2016-08-01