| Site | Priority | Project Description | Status | Estimated Completion Date |
| --- | --- | --- | --- | --- |
| AE | III | Full Day Kinder Portables (2 ea.) | PSFA- will coordinate with District Architect for necessary site work. (Utilities, Piers, etc.) | Units are ready for delivery when piers are built per PSFA. |
| AE |  | Chapter I Bldg- Install Partition | Wall installation complete-Pending installation of door jams | Aug 15,2004 |
| AE |  | Principal Office | Door relocation | Work request on hold (not approved). |
| AE | VI | Nurses Office | Doorway to new office | Aug 31, 2004 |
| AE | II | Nurses Office | Install refrigeration unit | Waiting on doorway installer (contracted service) to schedule work. |
| AE |  | DABCC | Replace double wood doors | On hold per Mr. Chavez |
| AE |  | Mid-Bldg. | Locker removal | On Hold. |
| AE | IV | Water Supply | Back Flow Prevention, Device installation | On Hold |
| BE |  | Office | Cooling Upgrade to Refrigerated type. | Waiting on Approval from CMT. |
| CHE | IV | Barracks Bldg. Repairs | Metal door replaced | Will be replaced on a as need basis-No funds available for complete replacement. |
| CHE | VI | Barracks Bldg. Repairs | Partition for E-Wing office | Materials on order- Est. Completion Date July 20, 2004. |
| CHE | IV | Barracks Bldg. Repairs. | Flooring repairs (Rms. 208, 209,210) | In the process of securing price quotes for sub floor repair. |
| CHE | IV | Barracks Bldg. Repairs. | Bathroom floor repair | In the process of securing price quotes for contracted work. |
| CHE | IV | Barracks Bldg. Repairs | Repair porch ceiling | Materials order in progress- Est. Comp. Date Aug.10, 2004. |
| DT |  |  | Various floor covering replacement | Request on hold. |
| DV |  |  | Various floor covering replacement | Request on hold. |
| LU | II | Asbestos Abatement Project | Refinish floor, reinstall furniture. Abatement Complete- Floor Covering installation in progress. | Completed |
| LU |  | Irrigation Well | Replumbing for irrigation purposes | Request on hold. |
| LU |  | Wastewater System | Connect to Community System | June 2005 |
| LU |  | Temporary Parking on EBID, Right of way | Parking on drain levy will need to be rebuilt due to EBID- maintenance on drain. | Preparing paperwork necessary to obtain special use permit for property EBID- Aug 2004. |
| LM | IV | Barracks | Need sub floor repairs/renovations. Exterior wall repair/stucco. | Awaiting for direction and funding from CMT. |
| RS | VI | Teachers Lounge | Electrical service upgrade | Complete |
| SM | IV |  | Floor repairs to CR#30-31 | Complete |
| SM | IV | Wastewater System | Monitoring of system operation- Leach Fields are showing signs of failure. | Will continue monitoring and working with E.I.D to determine repair & schedule. |
| SP |  | Office Area | Counter top & floor covering replacement | Aug 15, 2004 |
| CMS | IV | Main building | Bathroom wall repair | Complete |
| GMS | III | C.O.Classrooms |  | Complete |
| GMS | III | Board Room | Carpet replacement | August 31,2004 |
| GMS | III |  | Carpet &ceramic tile replacement throughout bldg. | Est. Comp. Date Aug 3, 2004 |
| GMS |  | Support Service Portable | Preparing portable for relocation at Alliance Hospital. Demo repaired and textured walls, pending carpet. | Estimated completion date August 15, 2004 |
| Site | Priority | Project Description | Status | Estimated Completion Date |
| STM |  | Choir Room | Ceiling, Mechanical & Electrical | On Hold |
| GHS | II | Counselor’s Office | Repair | In Progress, Est.Comp. Date July 3, 2004 |
| GHS | III | Moreno’s Classroom | Doorway cut-pending Jam installation | Est. Comp. Date Aug 12, 2004 |
| GHS | VI | North Bldg. | Doorway cut-need Jam floor repairs | Comp. July 15, 2004 |
| GHS |  | Student Parking | Install fencing and lights. Lights Completed | Void per Mr. Foster |
| GHS | II | Asbestos Abatement Project-Main Bldg. | Remove furniture, remove hallway lockers, Demo old journalism office, paint classroom, refinish floors, re-install furniture, and reinstall lockers throughout campus. | Complete |
| GHS |  | Auto Mechanics Classroom Shop | Install lift (vehicle) | On Hold |
| GHS | IV | Wastewater treatment plant. | Need to replace main transfer pump | Pump on order |
| GHS | IV | Swimming pool | Circulation pump is in need to schedule work | Replacement unit on order-Aug 31,2004 |
| GHS |  | South side perimeter fence repairs | Replacement-estimated cost $8,000.00 | On hold for next years funding (SB-9) |
| STHS | IV | Replacement lockers for fire damaged unit | Will relocate units from Anthony Mid Bldg. | Est. Comp. Date Aug 31, 2004 |
| Motor Vehicle Shop |  |  | Complete Shop Expansion | On hold |
| Site | Priority | Project Description | Status | Estimated Completion Date |
| Motor Vehicle Shop |  | Auto Shop Supervisor | Build Office for Supervisor ( Transportation Clerk is in current office) | On hold |
| DP | III | Front office | Recarpet | complete |
| DP | III | Center barracks | Remodel center barracks into three classrooms | Project in design, Est. Comp. Date Aug 31, 2004 |
| DP | III | Conference room portable | Install partition in conference room portable | Material on order Aug 31, 2004 |
| DP | IV | Portables | Install water fountain in all portables | Work request under review |
| GAC | VI | Building Repairs | Miscellaneous mechanical & electrical repairs | In progress |
| GAC | VI | C-wing conference room | Demo complete floor covering complete-wall repair in progress | Est. Completion Date July 20, 2004 |
| GAC |  | Dining room | New floor covering, installation of temporary wall. | On Hold |