TO:		Richard Chavez, Associate Supt. for Support Services

FROM:		David F. Boyd, Construction Coordinator

DATE:		October 23, 2007

SUBJECT:	District Construction Update

PSCOC FUNDING Plus District 13% Bond Funds

Chaparral High School:

Phase I / Main Building – Project is 99% Complete

Closing out Project

Phase II / Wings Q & R – Project to start October 25, 2007

Contract Signed

Phase II / Playfields      – Project is 30% Complete

Phase II / Field Houses – Bid Documents to PSFA for Final Approval, November 15, 2007

North Valley Elementary School:

Under construction       – Project is 80% Complete

Project completion date February 15, 2008

Santa Teresa High School:

Gym 		            – Bid Documents to PSFA for Final Approval, October 19, 2007

Project will bid approximately December 2007

100% Bond Funds

Weight Room	            – Project is 99% Complete

Closing out Project

Parking 	            – Project is in Design

$600,000.00 NM Dept. of Transportation Funds

Gadsden Middle School:

Addition/Remodel	– Bid Documents to PSFA for Final Approval, November 15, 2007

Project will bid approximately December 2007

Page 1 of 3

Gadsden High School:

Admin/Lib, Gym		– Bid Documents to PSFA for Final Approval, December 2007

Project will bid approximately February 2008

Anthony Elementary School:

Walk Paths 		– Project is 100% Complete

Basketball/Canopy	– Project is 100% Complete

Governor Distributions of $100,000.00

2E Roofing (PSCOC) 	– Santa Teresa High School is 90% Complete

BOND PROCEEDS

Anthony Elementary School:

Boiler Replacement 	– Out to Bid

(Old Main Bldg.)

Fan Coil Upgrade 	– Out to Bid

(Primary Bldg.)

Santa Teresa Middle School:

Parking Lot Re-stripping – Will Change Order this work with Riverside Elementary Student Drop-off

Geothermal Recirculating – Out to Bid

Pump

Northern On-Track Pre-K:

Under Construction 	– Project is 100% Complete

Closing out Project

Gadsden Administration Complex:

HVAC Replacement 	– Out to Bid

Re-roofing		– Project is 10% Complete

Desert Trail Elementary School:

Playground Equipment 	– Project is Complete

Gadsden Middle School, La Mesa & San Miguel Elem. Schools:

Boiler Replacement 	– Project is Complete

Page 2 of 3

Desert View Elementary School:

Landscaping 		– HB 622 Need account access from Finance Dept

Chaparral Elementary School:

Landscaping 		– HB 622 Need account access from Finance Dept.

Berino, Desert Trail, Loma Linda Elementary Schools and Chaparral Middle School:

2E Roofing 		– Project in Design

(PSCOC Funding)

Physical Plant Complex:

Fueling Station 		– In Design by Engineers

District Food Service Warehouse:

Warehouse 		– In Design due to Bid in January 2008

Page 3 of 3

# Text boxes

# CONSTRUCTION OFFICE

## David F. Boyd

## Construction Coordinator

1325 W. Washington St.

P.O. Drawer 70

Anthony, NM  88021

Phone (505) 882-6925

Fax (505) 882-2508