## SPCE.PROJ. PENDING
Site | WO# | Project Description |  | Estimated Completion Date
DP | 91169 | Portable 32DW | Provide electrical, water and sewer and install evaporative a/c unit. | Complete
91170
91171
| 94720 |  | Need to redeck portable when abatement is complete. | Completed Abatement - Pending Floor and Tile
DP | 97404 |  | Removal and concrete cutting.
DT | 97410 | Sanchez Portable | Concrete around portable and surrounding area. | 2013-01-01
GHS | 50365 | Leadership Project | Requested by Mr. Grace on behalf of the Facilities Goal Team for the | Will plan for Summer Project
Entire Campus-Metal doors, rails, poles need to be painted maroon.
GHS/GMS |  | Wastewater Line | Renewing permit for placement of utilities in public right of way | IBUC Permit renewed - selection contractor
|  |  | So we can obtain a work permit to repair the line suspended on | and schedule of repair in progress.
|  |  | the River Crossing. | Scheduled Completion April 2013
LU |  | Classrooms | Painting classrooms as contractors finish remodeling | Phase 1 complete, pending completion of
contractors for 2nd phase.
MQ | 79890 | Playing Fields | Provide water for irrigation of playing fields. | Started on project - Pending Summer
Need to install new irrigation system.
MQ |  | Multi-Purpose Room | VCT Floor covering to be replaced with new. | 2013-04-01
RS | 93203 | Mobile Home Space | New fence will be installed in this area to store equipment | 65% Complete grounds work and tree removal
(i.e. Tractor, District Vehicle and Lawnmower)
RS | 97414 | Grounds | Need to remove shrubs (safety) | 2013-02-13
District Wide | 96024 | Baseball/Softball Fields | Purchase and Installation of new scoreboards. | 2013-04-01
CHS,GHS,STHS | 96027
96543
96016
96526
STHS |  | New Laser Machine | Install power and vent . | Air blowers were recommended by Company
purchased and installed. Now pending exhaust
motors will order and install.