## SPCE.PROJ. PENDING
Site | WO# | Project Description |  | Estimated Completion Date
AE-Pre-K | 99575 | Threat Assessment | Installation of new fencing | 2013-05-01
AE-Pre-K | 100051 | ADA | Pour new sidewalk | 2013-05-01
DT | 100536 | Threat Assessment | Installation of new fencing w/gates | 2013-05-01
GAC | 99743 | Electrician/Plumber | Purchase of new Morgan Building | On order
GHS | 99864 | Soccer Field | Demo and removal of existing concrete and pour new concrete | In Progress
w/ADA requirements along w/new sidewalk
GHS | 50365 | Leadership Project | Requested by Mr. Grace on behalf of the Facilities Goal Team for the | Completed - Spring Break
Entire Campus-Metal doors, rails, poles need to be painted maroon.
GHS/GMS |  | Wastewater Line | Renewing permit for placement of utilities in public right of way | IBUC & NMDOT Permit renewed -
|  |  | So we can obtain a work permit to repair the line suspended on | BID opening April 18, 2013
|  |  | the River Crossing. | Scheduled Completion July 2013
LU |  | Classrooms | Painting classrooms as contractors finish remodeling | Phase 1 complete, pending completion of
contractors for 2nd phase.
MQ | 79890 | Playing Fields | Provide water for irrigation of playing fields. | Started on project - Pending Summer
Need to install new irrigation system.
MQ | 85440 | Multi-Purpose Room | VCT Floor covering to be replaced with new. | 2013-04-01
STE | 97636 | Art Room | Purchase of new Morgan Building | On order
RS | 93203 | Mobile Home Space | New fence will be installed in this area to store equipment | 65% Complete grounds work and tree removal
(i.e. Tractor, District Vehicle and Lawnmower)
District Wide | 96024 | Baseball/Softball Fields | Purchase and Installation of new scoreboards. | 2013-04-01
CHS,STHS | 96016
GHS | 96027 |  |  | STHS - Complete
| 96543 |  |  | GHS - Complete
96526
District Wide |  | Pre-K Centers | Build raised planters at sites. | 2013-05-01
AE, CHS
LM