## SPCE.PROJ. PENDING
Site | WO# | Project Description |  | Estimated Completion Date
DT | 102469 | Portable | Portable Relocation # 39 DM from San Miguel | Portable Relocation/Utilities Complete
Flooring Complete and Sidewalks Pending
GMS | 108800 | Gym | Relocate scoreboard | 2013-10-01
GMS |  | Front Campus | Remove mulberry trees from planters and prep for planting. | In Progress
LM - Daycare | 105965 | Daycare Area | Painting and clean up of daycare rooms. | Complete
MQ | 79890 | Playing Fields | Provide water for irrigation of playing fields. | Started on project - Pending Summer
Need to install new irrigation system.
MQ |  | Nurses Office | Install additional double doors in office. | In Progress
STE | 97636 | Art Room | Purchase of new Morgan Building | Complete
District Wide | 99576 | Pre-K Centers | Build raised planters at sites. | 2013-08-01
AE, CHS | 99797
LM | 104223