## SPCE.PROJ. PENDING
Site | WO# | Project Description |  | Estimated Completion Date
CHE | 112135 | Bus Pick-up | Replace 4Ft with 6FT fence | As per CMT, it was agreed fence does not need
to be replaced.
CH-Pre-K |  | Playground | Replace sand with Engineered Wood Fiber | 2014-03-28
Fall Area
CHS | 93777 | Soccer Field | Install canopy shades | 2014-08-01
GHS | 109343 | Baseball Field | 6' Fence around boys baseball batting cages | 2014-03-01
GHS | 110768 | Baseball Field | Install new batting cages | 80% Complete
GMS | 108222 | Front Campus | Remove mulberry trees from planters and prep for planting. | Removal of trees & planting by others - Complete
Working on providing water source and electrical
for irrigation system.
GMS | 110835 | Permit | Acquire "Right of Use Permit" for 40ft of left bank of Anthony Drain | Permit Approved by EBID on 11/22/13
|  |  | for parking access, fence and landscaping. | Filing of Drain by EBID to begin January 2014
Estimate completion 2/28/14
MQ | 79890 | Playing Fields | Provide water for irrigation of playing fields. | Started on project - Pending Summer
|  |  | Need to install new irrigation system. | 25% Complete
MQ |  | Nurses Office | Install additional double doors in office. | 80% Complete
(pending door closers)
MQ | 111219 | Septic Tank | Demolish and remove abandoned septic tank and pumps. | 2014-04-01
STE | 112234 | Bus Turnaround | Metal canopy shades for students | 2014-08-01
STMS | 112136 | Fire Hydrants | Replacement of (5) Fire Hydrants | Tentative during Spring Break