## SPCE.PROJ. PENDING
Site | WO# | Project Description |  | Estimated Completion Date
CH-Pre-K | 117023 | Playground | New cinder block barrier to separate sandbox from wood chips. | 2014-08-01
Pending PO
CHS | 93777 | Soccer Field | Install canopy shades | In Progress - 40% Complete
CHS | 116042 | Amphitheater | Remove and replace a section of concrete that is lifting. | Complete
CHS | 119228 | Running Track | Repair worn rubberized surface, apply 2 coats to running track | Repairs and application of 2 coats of structural
|  |  | and stripe running track. | spray complete. Stripping scheduled for 8/27/14
GHS | 116990 | Boys Baseball Field | Remove grass from diamond and replace with sod. | 80% complete, pending primary screening
GMS | 108222 | Front Campus | Remove mulberry trees from planters and prep for planting. | Removal of trees & planting by others - Complete
Working on providing water source and electrical
for irrigation system.
GMS/C-Wing | 117895 | Athletic Dept. | New Tuff Shed | 2014-09-01
GMS | 112149 | Gym | Installation of new boiler | Complete
GMS | 117147 | PE Dressing Rooms | Replacement of lockers in Boy & Girls | Complete
MQ | 111219 | Septic Tank | Demolish and remove abandoned septic tank and pumps. | Complete
PPD | 117144 | Auto Shop | New 20' x 36 x 6" concrete pad | 2014-08-29
STE | 112234 | Bus Turnaround | Metal canopy shades for students | 2014-08-01