## SPCE.PROJ. PENDING
Site | WO# | Project Description |  | Estimated Completion Date
CH-Pre-K | 117023 | Playground | New cinder block barrier to separate sandbox from wood chips. | 2014-08-01
Pending PO
CHS | 93777 | Soccer Field | Install canopy shades | Complete
CHS | 119228 | Running Track | Repair worn rubberized surface, apply 2 coats to running track | Complete
and stripe running track.
GHS | 116990 | Boys Baseball Field | Remove grass from diamond and replace with sod. | Complete
GMS | 108222 | Front Campus | Remove mulberry trees from planters and prep for planting. | Complete
GMS/C-Wing | 117895 | Athletic Dept. | New Tuff Shed | Complete
PPD | 117144 | Auto Shop | New 20' x 36 x 6" concrete pad | Complete
STE | 112234 | Bus Turnaround | Metal canopy shades for students | Complete
DT | 122898 | Portable 412 | Remodel restroom | 2014-10-01
DT | 122915 |  | Purchase Tuff Shed for storage | 2014-10-01
LL | 122752 | Portable 1A & 1B | Remodel of restroom /storage room for washer and dryer, redo floor, | 2014-11-01
| 122754 |  | paint interior and exterior.
122796
122774
122799
122914
GMS | 116703 | Baseball Field | (2) Batting Cages | 2014-12-01
STHS | 120627 | Baseball Field | (7) Batting Cages | 2015-02-01