## SPCE.PROJ. PENDING
Site | WO# | Project Description |  | Estimated Completion Date
LL | 122752 | Portable 1A & 1B | Remodel of restroom /storage room for washer and dryer, redo floor, | Project complete March 25, 2015
| 122754 -Plumber |  | paint interior and exterior.
122796
122774 - Electrical
122799
126362
122798
128395
122914
GMS | 125856 | Baseball Field | New Scoreboard | Completed 2/9/15
STHS | 124792 | Football Field | New Scoreboard | 2015-03-01
STHS | 127644 | Softball Field | Batting cages for softball field please see Ms Contreras or Rick | 2015-05-30
GHS | 125861 | Softball Field | Batting cages for Softball Field | 2015-03-31
CHS | 116932 | Softball Field | Batting cages for Softball Field | 2015-04-30
Alta Vista ECHS |  | C-Wing | Remodeling - Change signs, Windows, Asbestos Abatement-New Flooring | 2015-03-31
C-Wing
STHS |  | Nurses Portable | Remodeling Clinical De Familia side for School Nurses, installation of | 2015-08-01
new restroom.
GAC - Prek | 127302 | Kitchen - Serving Area | Build a counter with sink and wall cabinets. | 2015-06-01